## Sheet1
Verification of | Preconditions | To be Done And Definition of Done | Date | Status
Implement the modified State machine for Humidity sensor | Sensor Testing with original state machine | Successfully able to get the state machine working with proper values | 2020-04-16 | Passed
Display the humidity values on the mobile app and the lcd display with proper logging | Getting correct values from the sensor with proper i2c initilialization and interrupt functionality | Logs and displays humidity on client mobile application with updated values | 2020-04-18 | Passed
Implement man in the middle attack protection | Getting pairing keys same on both client and server | Able to successfully bond with the client with bonding information being stored once previously bonded | 2020-04-19 | Passed
Persistant data implementation and testing for humidity sensor | Able to bond with the client | Being able to use the flash load and flash save functions to display and store the sensor obtained values | 2020-04-21 | Passed
Interfacing air quality sensor with the board and observe correct signlas on the logic analyzer | Initialize correct pins and port with unused pins connected as required in datasheet | Able to get clock and signals on logic analyser with proper acknowledgement | 2020-04-21 | Partially Done
Get correct values from Air quality sensor to be displayed on the client side by writing necessary state machine with persistent data | Address is acknowledged with init being succesful and sensor boots in ap[lication mode with appropriate firmware present | Able to get updating readings of ppm which is observed in ALG_REG | 2020-04-24 | To be Done
Perform DFU | Close connection | Perform routines for the connection to enter to DFU OTA mode | 2020-04-25 | To be Done
Integrate all sensors and validation of project | Able to get individual state machine working for both the sensors successfully along with ble stack implementation for basic temp sensor | Able to integrate the sensors to get appropriat readings with the ability to store them and retrieve back from the flash | 2020-04-25 | To be Done